## Task Registry
ID | Feature | Story | Task Title | Priority | Story Points | Status | Sprint | Assignee | Dependencies | Notes
F1-T01 | F1 | S-PDF | MD→PDF Rendering Engine | P0 | 5 | Not Started | Sprint 1
F1-T02 | F1 | S-PDF | Caption Generator Module | P0 | 3 | Not Started | Sprint 1
F1-T03 | F1 | S-PDF | TOC / TOA Auto-Builder | P0 | 5 | Not Started | Sprint 2
F1-T04 | F1 | S-PDF | Exhibit Bates Stamper | P0 | 5 | Not Started | Sprint 2
F1-T05 | F1 | S-PDF | PDF/A Compliance Validator | P0 | 3 | Not Started | Sprint 3
F2-T01 | F2 | S-MBP | Neural Intent Classifier | P0 | 8 | Not Started | Sprint 2
F2-T02 | F2 | S-MBP | Ensemble Scoring Pipeline | P0 | 5 | Not Started | Sprint 3
F2-T03 | F2 | S-MBP | Self-Evolution Feedback Loop | P0 | 8 | Not Started | Sprint 4
F2-T04 | F2 | S-MBP | BM25+ Retrieval Upgrade | P0 | 5 | Not Started | Sprint 3
F2-T05 | F2 | S-MBP | Confidence Calibration Module | P0 | 3 | Not Started | Sprint 4
F3-T01 | F3 | S-DRV | 6-Drive Inventory Scanner | P1 | 5 | Not Started | Sprint 1
F3-T02 | F3 | S-DRV | Global Content-Based Dedup | P1 | 8 | Not Started | Sprint 2
F3-T03 | F3 | S-DRV | Content Classifier Engine | P1 | 5 | Not Started | Sprint 2
F3-T04 | F3 | S-DRV | Lane-Aware File Router | P1 | 5 | Not Started | Sprint 3
F3-T05 | F3 | S-DRV | Backup Manifest Generator | P1 | 3 | Not Started | Sprint 3
F4-T01 | F4 | S-SKL | Skill Registry & Discovery | P0 | 5 | Not Started | Sprint 1
F4-T02 | F4 | S-SKL | Semantic Versioning Engine | P0 | 3 | Not Started | Sprint 2
F4-T03 | F4 | S-SKL | Skill Chaining Orchestrator | P0 | 8 | Not Started | Sprint 3
F4-T04 | F4 | S-SKL | Auto-Evolution Daemon | P0 | 8 | Not Started | Sprint 4
F4-T05 | F4 | S-SKL | Skill Marketplace API | P0 | 5 | Not Started | Sprint 5
F4-T06 | F4 | S-SKL | Dependency Resolution Graph | P0 | 5 | Not Started | Sprint 3
F5-T01 | F5 | S-FIL | Auto-Assembler Engine | P1 | 8 | Not Started | Sprint 3
F5-T02 | F5 | S-FIL | SCAO Form Filler | P1 | 5 | Not Started | Sprint 4
F5-T03 | F5 | S-FIL | Pre-Filing QA Sweep | P1 | 5 | Not Started | Sprint 4
F5-T04 | F5 | S-FIL | E-Filing Package Builder | P1 | 5 | Not Started | Sprint 5
F5-T05 | F5 | S-FIL | Service Proof Tracker | P1 | 3 | Not Started | Sprint 5
F6-T01 | F6 | S-RAG | Vector Store Indexer | P1 | 8 | Not Started | Sprint 4
F6-T02 | F6 | S-RAG | Cross-Encoder Reranker | P1 | 5 | Not Started | Sprint 5
F6-T03 | F6 | S-RAG | Knowledge Graph RAG Bridge | P1 | 8 | Not Started | Sprint 5
F6-T04 | F6 | S-RAG | Hybrid Search Merger | P1 | 5 | Not Started | Sprint 6
F6-T05 | F6 | S-RAG | Citation Grounding Module | P1 | 5 | Not Started | Sprint 6
F7-T01 | F7 | S-EVO | Daemon Framework Core | P2 | 8 | Not Started | Sprint 5
F7-T02 | F7 | S-EVO | Quality Feedback Collector | P2 | 5 | Not Started | Sprint 6
F7-T03 | F7 | S-EVO | Self-Healing Error Corrector | P2 | 8 | Not Started | Sprint 7
F7-T04 | F7 | S-EVO | Performance Regression Guard | P2 | 5 | Not Started | Sprint 7
F7-T05 | F7 | S-EVO | Evolution Rollback Manager | P2 | 5 | Not Started | Sprint 8
F7-T06 | F7 | S-EVO | Canary Deploy Pipeline | P2 | 3 | Not Started | Sprint 8
F8-T01 | F8 | S-PRD | Multi-Tenant Isolation Layer | P2 | 8 | Not Started | Sprint 6
F8-T02 | F8 | S-PRD | Jurisdiction Plugin Framework | P2 | 8 | Not Started | Sprint 7
F8-T03 | F8 | S-PRD | Monetization Billing Engine | P2 | 5 | Not Started | Sprint 8
F8-T04 | F8 | S-PRD | Onboarding Wizard UI | P2 | 5 | Not Started | Sprint 8
F8-T05 | F8 | S-PRD | Usage Analytics Dashboard | P2 | 3 | Not Started | Sprint 9
F8-T06 | F8 | S-PRD | License Key Manager | P2 | 3 | Not Started | Sprint 9

## Sprint Planner
Sprint # | Start Date | End Date | Planned SP | Actual SP | Velocity | Features in Sprint | Completion %
1 | 2025-07-14 | 2025-07-27 | 18 | 0 |  | F1, F3, F4
2 | 2025-07-28 | 2025-08-10 | 34 | 0 |  | F1, F2, F3, F4
3 | 2025-08-11 | 2025-08-24 | 42 | 0 |  | F1, F2, F3, F4, F5
4 | 2025-08-25 | 2025-09-07 | 37 | 0 |  | F2, F4, F5, F6
5 | 2025-09-08 | 2025-09-21 | 34 | 0 |  | F4, F5, F6, F7
6 | 2025-09-22 | 2025-10-05 | 23 | 0 |  | F6, F7, F8
7 | 2025-10-06 | 2025-10-19 | 21 | 0 |  | F7, F8
8 | 2025-10-20 | 2025-11-02 | 18 | 0 |  | F7, F8
9 | 2025-11-03 | 2025-11-16 | 6 | 0 |  | F8

## Burndown
Sprint | Ideal Remaining | Actual Remaining
1
2
3
4
5
6
7
8
9
📊 Chart Note:
Select A1:C10 → Insert → Line Chart to visualize burndown. Ideal = straight line, Actual = progress curve.

## Dependency Matrix
Feature ↓ \ Depends On → | F1 | F2 | F3 | F4 | F5 | F6 | F7 | F8
F1 | bar: F1 to F8
F2 | F2: —; F4: →; F6: ←
F3 | bar: F1 to F8
F4 | bar: F2; F4; F6
F5 | F1: →; F5: —; F8: ←
F6 | F2: →; F4: →; F6: —; F7: ←
F7 | bar: F1 to F8
F8 | bar: F5; F8
Critical Paths:
Path A: F4 → F2 → F6 → F7 (Skill Framework enables MANBEARPIG enables RAG enables Self-Evolution)
Path B: F1 → F5 → F8 (PDF Tooling enables Filing Automation enables Productization)
F3 (Drive Reorganization): Independent — can run in parallel with all paths

## Dashboard
🏗️ PROJECT COMMAND CENTER
Total Tasks | Done | In Progress | Blocked | Not Started | % Complete
📋 Feature Breakdown
Feature ID | Feature Name | Total Tasks | Done | In Progress | Story Points
F1 | PDF Tooling
F2 | MANBEARPIG v10
F3 | Drive Reorganization
F4 | Skill Framework
F5 | Filing Automation
F6 | RAG Pipeline
F7 | Self-Evolution
F8 | Productization
TOTAL | All Features
🚀 Sprint Velocity Trend
Sprint | Planned SP | Actual SP | Velocity | Cumulative SP | % of Total
1
2
3
4
5
6
7
8
9